## Data
Reporting date | Activity ID | Activity name | Activity budget | Planned progress % | Actual progress % | AC cumulative | Notes
2011-11-08 | A01 | Sondering | 620 | 100 | 100 | 620
2011-11-08 | A02 | Inrichting | 2265.49 | 100 | 100 | 2265.49
2011-11-08 | A03 | Bouwput + Kelders | 26416.96 | 100 | 57.9997 | 20252.96
2011-11-08 | A04 | Bouw rioleringen | 31847.8 | 0 | 0 | 0
2011-11-08 | A05 | Afbraakwerken | 8100.4 | 100 | 100 | 10935.6
2011-11-08 | A06 | Ruwbouw | 121519.05 | 0 | 0 | 0
2011-11-08 | A07 | Wachtgevel | 9790.35 | 0 | 0 | 0
2011-11-08 | A08 | Dakisolatie | 5545.19 | 0 | 0 | 0
2011-11-08 | A09 | Dakbedekking & Zinkwerk | 44145.98 | 0 | 0 | 0
2011-11-08 | A10 | Buitenschrijnwerk | 71547.18 | 0 | 0 | 0
2011-11-08 | A11 | Sanitaire technieken | 33402.44 | 0 | 0 | 0
2011-11-08 | A12 | Electriciteitstechnieken | 29082.43 | 0 | 0 | 0
2011-11-08 | A13 | Ventilatietechnieken | 6392 | 0 | 0 | 0
2011-11-08 | A14 | Trappen en Deuren | 9686.84 | 0 | 0 | 0
2011-11-08 | A15 | Keukens | 4666.79 | 0 | 0 | 0
2011-11-08 | A16 | Pleisterwerken | 16596.74 | 0 | 0 | 0
2011-11-08 | A17 | Buitenpleisterwerk | 34664.75 | 0 | 0 | 0
2011-11-08 | A18 | Afwerking Ventilatie | 3196 | 0 | 0 | 0
2011-11-08 | A19 | Plaatsen Sanitaire Toestellen & Radiatoren | 11133.75 | 0 | 0 | 0
2011-11-08 | A20 | Afwerking | 9693.74 | 0 | 0 | 0
2011-11-08 | A21 | Chapewerken | 14216.05 | 0 | 0 | 0
2011-11-08 | A22 | Vloeren | 21777.21 | 0 | 0 | 0
2011-11-08 | A23 | Buitenaanleg | 6737.19 | 0 | 0 | 0
2011-11-08 | A24 | Schilderwerken | 9072.52 | 0 | 0 | 0
2011-11-08 | A25 | Opkuis | 293.44 | 0 | 0 | 0
2011-12-06 | A01 | Sondering | 620 | 100 | 100 | 620
2011-12-06 | A02 | Inrichting | 2265.49 | 100 | 100 | 2265.49
2011-12-06 | A03 | Bouwput + Kelders | 26416.96 | 100 | 100 | 38744.96
2011-12-06 | A04 | Bouw rioleringen | 31847.8 | 100 | 47.4997 | 16985.4
2011-12-06 | A05 | Afbraakwerken | 8100.4 | 100 | 100 | 10935.6
2011-12-06 | A06 | Ruwbouw | 121519.05 | 34.9995 | 0 | 0
2011-12-06 | A07 | Wachtgevel | 9790.35 | 0 | 0 | 0
2011-12-06 | A08 | Dakisolatie | 5545.19 | 0 | 0 | 0
2011-12-06 | A09 | Dakbedekking & Zinkwerk | 44145.98 | 0 | 0 | 0
2011-12-06 | A10 | Buitenschrijnwerk | 71547.18 | 0 | 0 | 0
2011-12-06 | A11 | Sanitaire technieken | 33402.44 | 0 | 0 | 0
2011-12-06 | A12 | Electriciteitstechnieken | 29082.43 | 0 | 0 | 0
2011-12-06 | A13 | Ventilatietechnieken | 6392 | 0 | 0 | 0
2011-12-06 | A14 | Trappen en Deuren | 9686.84 | 0 | 0 | 0
2011-12-06 | A15 | Keukens | 4666.79 | 0 | 0 | 0
2011-12-06 | A16 | Pleisterwerken | 16596.74 | 0 | 0 | 0
2011-12-06 | A17 | Buitenpleisterwerk | 34664.75 | 0 | 0 | 0
2011-12-06 | A18 | Afwerking Ventilatie | 3196 | 0 | 0 | 0
2011-12-06 | A19 | Plaatsen Sanitaire Toestellen & Radiatoren | 11133.75 | 0 | 0 | 0
2011-12-06 | A20 | Afwerking | 9693.74 | 0 | 0 | 0
2011-12-06 | A21 | Chapewerken | 14216.05 | 0 | 0 | 0
2011-12-06 | A22 | Vloeren | 21777.21 | 0 | 0 | 0
2011-12-06 | A23 | Buitenaanleg | 6737.19 | 100 | 0 | 0
2011-12-06 | A24 | Schilderwerken | 9072.52 | 0 | 0 | 0
2011-12-06 | A25 | Opkuis | 293.44 | 0 | 0 | 0
2012-01-10 | A01 | Sondering | 620 | 100 | 100 | 620
2012-01-10 | A02 | Inrichting | 2265.49 | 100 | 100 | 2265.49
2012-01-10 | A03 | Bouwput + Kelders | 26416.96 | 100 | 100 | 38744.96
2012-01-10 | A04 | Bouw rioleringen | 31847.8 | 100 | 100 | 39279
2012-01-10 | A05 | Afbraakwerken | 8100.4 | 100 | 100 | 10935.6
2012-01-10 | A06 | Ruwbouw | 121519.05 | 59.9997 | 37.7773 | 48607.05
2012-01-10 | A07 | Wachtgevel | 9790.35 | 0 | 0 | 0
2012-01-10 | A08 | Dakisolatie | 5545.19 | 0 | 0 | 0
2012-01-10 | A09 | Dakbedekking & Zinkwerk | 44145.98 | 0 | 0 | 0
2012-01-10 | A10 | Buitenschrijnwerk | 71547.18 | 0 | 0 | 0
2012-01-10 | A11 | Sanitaire technieken | 33402.44 | 0 | 0 | 0
2012-01-10 | A12 | Electriciteitstechnieken | 29082.43 | 0 | 0 | 0
2012-01-10 | A13 | Ventilatietechnieken | 6392 | 0 | 0 | 0
2012-01-10 | A14 | Trappen en Deuren | 9686.84 | 0 | 0 | 0
2012-01-10 | A15 | Keukens | 4666.79 | 0 | 0 | 0
2012-01-10 | A16 | Pleisterwerken | 16596.74 | 0 | 0 | 0
2012-01-10 | A17 | Buitenpleisterwerk | 34664.75 | 0 | 0 | 0
2012-01-10 | A18 | Afwerking Ventilatie | 3196 | 0 | 0 | 0
2012-01-10 | A19 | Plaatsen Sanitaire Toestellen & Radiatoren | 11133.75 | 0 | 0 | 0
2012-01-10 | A20 | Afwerking | 9693.74 | 0 | 0 | 0
2012-01-10 | A21 | Chapewerken | 14216.05 | 0 | 0 | 0
2012-01-10 | A22 | Vloeren | 21777.21 | 0 | 0 | 0
2012-01-10 | A23 | Buitenaanleg | 6737.19 | 100 | 100 | 11453.19
2012-01-10 | A24 | Schilderwerken | 9072.52 | 0 | 0 | 0
2012-01-10 | A25 | Opkuis | 293.44 | 0 | 0 | 0
2012-02-14 | A01 | Sondering | 620 | 100 | 100 | 620
2012-02-14 | A02 | Inrichting | 2265.49 | 100 | 100 | 2265.49
2012-02-14 | A03 | Bouwput + Kelders | 26416.96 | 100 | 100 | 38744.96
2012-02-14 | A04 | Bouw rioleringen | 31847.8 | 100 | 100 | 39279
2012-02-14 | A05 | Afbraakwerken | 8100.4 | 100 | 100 | 10935.6
2012-02-14 | A06 | Ruwbouw | 121519.05 | 84.9999 | 57.2219 | 78987.05
2012-02-14 | A07 | Wachtgevel | 9790.35 | 0 | 0 | 0
2012-02-14 | A08 | Dakisolatie | 5545.19 | 0 | 0 | 0
2012-02-14 | A09 | Dakbedekking & Zinkwerk | 44145.98 | 0 | 0 | 0
2012-02-14 | A10 | Buitenschrijnwerk | 71547.18 | 0 | 0 | 0
2012-02-14 | A11 | Sanitaire technieken | 33402.44 | 0 | 0 | 0
2012-02-14 | A12 | Electriciteitstechnieken | 29082.43 | 0 | 0 | 0
2012-02-14 | A13 | Ventilatietechnieken | 6392 | 0 | 0 | 0
2012-02-14 | A14 | Trappen en Deuren | 9686.84 | 0 | 0 | 0
2012-02-14 | A15 | Keukens | 4666.79 | 0 | 0 | 0
2012-02-14 | A16 | Pleisterwerken | 16596.74 | 0 | 0 | 0
2012-02-14 | A17 | Buitenpleisterwerk | 34664.75 | 0 | 0 | 0
2012-02-14 | A18 | Afwerking Ventilatie | 3196 | 0 | 0 | 0
2012-02-14 | A19 | Plaatsen Sanitaire Toestellen & Radiatoren | 11133.75 | 0 | 0 | 0
2012-02-14 | A20 | Afwerking | 9693.74 | 0 | 0 | 0
2012-02-14 | A21 | Chapewerken | 14216.05 | 0 | 0 | 0
2012-02-14 | A22 | Vloeren | 21777.21 | 0 | 0 | 0
2012-02-14 | A23 | Buitenaanleg | 6737.19 | 100 | 100 | 11453.19
2012-02-14 | A24 | Schilderwerken | 9072.52 | 0 | 0 | 0
2012-02-14 | A25 | Opkuis | 293.44 | 0 | 0 | 0
2012-03-06 | A01 | Sondering | 620 | 100 | 100 | 620
2012-03-06 | A02 | Inrichting | 2265.49 | 100 | 100 | 2265.49
2012-03-06 | A03 | Bouwput + Kelders | 26416.96 | 100 | 100 | 38744.96
2012-03-06 | A04 | Bouw rioleringen | 31847.8 | 100 | 100 | 39279
2012-03-06 | A05 | Afbraakwerken | 8100.4 | 100 | 100 | 10935.6
2012-03-06 | A06 | Ruwbouw | 121519.05 | 100 | 68.8886 | 97215.05
2012-03-06 | A07 | Wachtgevel | 9790.35 | 0 | 0 | 0
2012-03-06 | A08 | Dakisolatie | 5545.19 | 0 | 0 | 0
2012-03-06 | A09 | Dakbedekking & Zinkwerk | 44145.98 | 0 | 0 | 0
2012-03-06 | A10 | Buitenschrijnwerk | 71547.18 | 0 | 0 | 0
2012-03-06 | A11 | Sanitaire technieken | 33402.44 | 0 | 0 | 0
2012-03-06 | A12 | Electriciteitstechnieken | 29082.43 | 0 | 0 | 0
2012-03-06 | A13 | Ventilatietechnieken | 6392 | 0 | 0 | 0
2012-03-06 | A14 | Trappen en Deuren | 9686.84 | 0 | 0 | 0
2012-03-06 | A15 | Keukens | 4666.79 | 0 | 0 | 0
2012-03-06 | A16 | Pleisterwerken | 16596.74 | 0 | 0 | 0
2012-03-06 | A17 | Buitenpleisterwerk | 34664.75 | 0 | 0 | 0
2012-03-06 | A18 | Afwerking Ventilatie | 3196 | 0 | 0 | 0
2012-03-06 | A19 | Plaatsen Sanitaire Toestellen & Radiatoren | 11133.75 | 0 | 0 | 0
2012-03-06 | A20 | Afwerking | 9693.74 | 0 | 0 | 0
2012-03-06 | A21 | Chapewerken | 14216.05 | 0 | 0 | 0
2012-03-06 | A22 | Vloeren | 21777.21 | 0 | 0 | 0
2012-03-06 | A23 | Buitenaanleg | 6737.19 | 100 | 100 | 11453.19
2012-03-06 | A24 | Schilderwerken | 9072.52 | 0 | 0 | 0
2012-03-06 | A25 | Opkuis | 293.44 | 0 | 0 | 0
2012-04-10 | A01 | Sondering | 620 | 100 | 100 | 620
2012-04-10 | A02 | Inrichting | 2265.49 | 100 | 100 | 2265.49
2012-04-10 | A03 | Bouwput + Kelders | 26416.96 | 100 | 100 | 38744.96
2012-04-10 | A04 | Bouw rioleringen | 31847.8 | 100 | 100 | 39279
2012-04-10 | A05 | Afbraakwerken | 8100.4 | 100 | 100 | 10935.6
2012-04-10 | A06 | Ruwbouw | 121519.05 | 100 | 88.3332 | 127595.05
2012-04-10 | A07 | Wachtgevel | 9790.35 | 100 | 0 | 0
2012-04-10 | A08 | Dakisolatie | 5545.19 | 100 | 0 | 0
2012-04-10 | A09 | Dakbedekking & Zinkwerk | 44145.98 | 53.333 | 0 | 0
2012-04-10 | A10 | Buitenschrijnwerk | 71547.18 | 100 | 0 | 0
2012-04-10 | A11 | Sanitaire technieken | 33402.44 | 0 | 0 | 0
2012-04-10 | A12 | Electriciteitstechnieken | 29082.43 | 0 | 0 | 0
2012-04-10 | A13 | Ventilatietechnieken | 6392 | 0 | 0 | 0
2012-04-10 | A14 | Trappen en Deuren | 9686.84 | 0 | 0 | 0
2012-04-10 | A15 | Keukens | 4666.79 | 0 | 0 | 0
2012-04-10 | A16 | Pleisterwerken | 16596.74 | 0 | 0 | 0
2012-04-10 | A17 | Buitenpleisterwerk | 34664.75 | 53.3336 | 0 | 0
2012-04-10 | A18 | Afwerking Ventilatie | 3196 | 0 | 0 | 0
2012-04-10 | A19 | Plaatsen Sanitaire Toestellen & Radiatoren | 11133.75 | 0 | 0 | 0
2012-04-10 | A20 | Afwerking | 9693.74 | 0 | 0 | 0
2012-04-10 | A21 | Chapewerken | 14216.05 | 0 | 0 | 0
2012-04-10 | A22 | Vloeren | 21777.21 | 0 | 0 | 0
2012-04-10 | A23 | Buitenaanleg | 6737.19 | 100 | 100 | 11453.19
2012-04-10 | A24 | Schilderwerken | 9072.52 | 0 | 0 | 0
2012-04-10 | A25 | Opkuis | 293.44 | 0 | 0 | 0
2012-05-01 | A01 | Sondering | 620 | 100 | 100 | 620
2012-05-01 | A02 | Inrichting | 2265.49 | 100 | 100 | 2265.49
2012-05-01 | A03 | Bouwput + Kelders | 26416.96 | 100 | 100 | 38744.96
2012-05-01 | A04 | Bouw rioleringen | 31847.8 | 100 | 100 | 39279
2012-05-01 | A05 | Afbraakwerken | 8100.4 | 100 | 100 | 10935.6
2012-05-01 | A06 | Ruwbouw | 121519.05 | 100 | 100 | 145823.05
2012-05-01 | A07 | Wachtgevel | 9790.35 | 100 | 0 | 0
2012-05-01 | A08 | Dakisolatie | 5545.19 | 100 | 0 | 0
2012-05-01 | A09 | Dakbedekking & Zinkwerk | 44145.98 | 88.3333 | 0 | 0
2012-05-01 | A10 | Buitenschrijnwerk | 71547.18 | 100 | 0 | 0
2012-05-01 | A11 | Sanitaire technieken | 33402.44 | 0 | 0 | 0
2012-05-01 | A12 | Electriciteitstechnieken | 29082.43 | 0 | 0 | 0
2012-05-01 | A13 | Ventilatietechnieken | 6392 | 0 | 0 | 0
2012-05-01 | A14 | Trappen en Deuren | 9686.84 | 0 | 0 | 0
2012-05-01 | A15 | Keukens | 4666.79 | 0 | 0 | 0
2012-05-01 | A16 | Pleisterwerken | 16596.74 | 0 | 0 | 0
2012-05-01 | A17 | Buitenpleisterwerk | 34664.75 | 100 | 0 | 0
2012-05-01 | A18 | Afwerking Ventilatie | 3196 | 0 | 0 | 0
2012-05-01 | A19 | Plaatsen Sanitaire Toestellen & Radiatoren | 11133.75 | 0 | 0 | 0
2012-05-01 | A20 | Afwerking | 9693.74 | 0 | 0 | 0
2012-05-01 | A21 | Chapewerken | 14216.05 | 0 | 0 | 0
2012-05-01 | A22 | Vloeren | 21777.21 | 0 | 0 | 0
2012-05-01 | A23 | Buitenaanleg | 6737.19 | 100 | 100 | 11453.19
2012-05-01 | A24 | Schilderwerken | 9072.52 | 0 | 0 | 0
2012-05-01 | A25 | Opkuis | 293.44 | 0 | 0 | 0
2012-05-21 | A01 | Sondering | 620 | 100 | 100 | 620 | INTERPOLATED test row (not a real report): straight line between the real reports of 01 May 2012 and 12 Jun 2012
2012-05-21 | A02 | Inrichting | 2265.49 | 100 | 100 | 2265.49 | INTERPOLATED test row (not a real report): straight line between the real reports of 01 May 2012 and 12 Jun 2012
2012-05-21 | A03 | Bouwput + Kelders | 26416.96 | 100 | 100 | 38744.96 | INTERPOLATED test row (not a real report): straight line between the real reports of 01 May 2012 and 12 Jun 2012
2012-05-21 | A04 | Bouw rioleringen | 31847.8 | 100 | 100 | 39279 | INTERPOLATED test row (not a real report): straight line between the real reports of 01 May 2012 and 12 Jun 2012
2012-05-21 | A05 | Afbraakwerken | 8100.4 | 100 | 100 | 10935.6 | INTERPOLATED test row (not a real report): straight line between the real reports of 01 May 2012 and 12 Jun 2012
2012-05-21 | A06 | Ruwbouw | 121519.05 | 100 | 100 | 145823.05 | INTERPOLATED test row (not a real report): straight line between the real reports of 01 May 2012 and 12 Jun 2012
2012-05-21 | A07 | Wachtgevel | 9790.35 | 100 | 47.2985 | 4630.69 | INTERPOLATED test row (not a real report): straight line between the real reports of 01 May 2012 and 12 Jun 2012
2012-05-21 | A08 | Dakisolatie | 5545.19 | 100 | 47.2985 | 2622.79 | INTERPOLATED test row (not a real report): straight line between the real reports of 01 May 2012 and 12 Jun 2012
2012-05-21 | A09 | Dakbedekking & Zinkwerk | 44145.98 | 93.8514 | 34.0548 | 13572.2 | INTERPOLATED test row (not a real report): straight line between the real reports of 01 May 2012 and 12 Jun 2012
2012-05-21 | A10 | Buitenschrijnwerk | 71547.18 | 100 | 47.2985 | 33840.73 | INTERPOLATED test row (not a real report): straight line between the real reports of 01 May 2012 and 12 Jun 2012
2012-05-21 | A11 | Sanitaire technieken | 33402.44 | 47.2985 | 0 | 0 | INTERPOLATED test row (not a real report): straight line between the real reports of 01 May 2012 and 12 Jun 2012
2012-05-21 | A12 | Electriciteitstechnieken | 29082.43 | 47.2985 | 0 | 0 | INTERPOLATED test row (not a real report): straight line between the real reports of 01 May 2012 and 12 Jun 2012
2012-05-21 | A13 | Ventilatietechnieken | 6392 | 47.2985 | 0 | 0 | INTERPOLATED test row (not a real report): straight line between the real reports of 01 May 2012 and 12 Jun 2012
2012-05-21 | A14 | Trappen en Deuren | 9686.84 | 0 | 0 | 0 | INTERPOLATED test row (not a real report): straight line between the real reports of 01 May 2012 and 12 Jun 2012
2012-05-21 | A15 | Keukens | 4666.79 | 0 | 0 | 0 | INTERPOLATED test row (not a real report): straight line between the real reports of 01 May 2012 and 12 Jun 2012
2012-05-21 | A16 | Pleisterwerken | 16596.74 | 0 | 0 | 0 | INTERPOLATED test row (not a real report): straight line between the real reports of 01 May 2012 and 12 Jun 2012
2012-05-21 | A17 | Buitenpleisterwerk | 34664.75 | 100 | 36.2622 | 12570.21 | INTERPOLATED test row (not a real report): straight line between the real reports of 01 May 2012 and 12 Jun 2012
2012-05-21 | A18 | Afwerking Ventilatie | 3196 | 0 | 0 | 0 | INTERPOLATED test row (not a real report): straight line between the real reports of 01 May 2012 and 12 Jun 2012
2012-05-21 | A19 | Plaatsen Sanitaire Toestellen & Radiatoren | 11133.75 | 0 | 0 | 0 | INTERPOLATED test row (not a real report): straight line between the real reports of 01 May 2012 and 12 Jun 2012
2012-05-21 | A20 | Afwerking | 9693.74 | 0 | 0 | 0 | INTERPOLATED test row (not a real report): straight line between the real reports of 01 May 2012 and 12 Jun 2012
2012-05-21 | A21 | Chapewerken | 14216.05 | 0 | 0 | 0 | INTERPOLATED test row (not a real report): straight line between the real reports of 01 May 2012 and 12 Jun 2012
2012-05-21 | A22 | Vloeren | 21777.21 | 0 | 0 | 0 | INTERPOLATED test row (not a real report): straight line between the real reports of 01 May 2012 and 12 Jun 2012
2012-05-21 | A23 | Buitenaanleg | 6737.19 | 100 | 100 | 11453.19 | INTERPOLATED test row (not a real report): straight line between the real reports of 01 May 2012 and 12 Jun 2012
2012-05-21 | A24 | Schilderwerken | 9072.52 | 0 | 0 | 0 | INTERPOLATED test row (not a real report): straight line between the real reports of 01 May 2012 and 12 Jun 2012
2012-05-21 | A25 | Opkuis | 293.44 | 0 | 0 | 0 | INTERPOLATED test row (not a real report): straight line between the real reports of 01 May 2012 and 12 Jun 2012

## About this file
Forecast test file: real project at 50 % physical completion
Project: Apartment Building (1), Belgium, DSLIB project C2014-05 (Batselier & Vanhoucke, 2015). 25 activities. Amounts in EUR.
Rows dated up to 01 May 2012: the project's real progress reports, unchanged (175 rows, 7 reports).
Rows dated 21 May 2012: INTERPOLATED, not a real report. No real report falls at 50 %: progress went from 37.1% (01 May 2012) to 64.4% (12 Jun 2012). Each activity's planned %, actual % and cost were taken 47.3% of the way between those two reports, which puts earned value at exactly 50 % of BAC.
Upload the 'Data' sheet in the EVM dashboard, then compare its forecasts with the answer key file.
Settings to enter in the app: currency EUR, baseline start 03-Oct-2011, baseline completion 15-Aug-2012, reporting frequency Irregular.