## Forecast check
Forecast check: what the dashboard should show vs what really happened
BAC (budget at completion) | 532410.29
Actual final cost (real, at completion) | 591410.53
Baseline completion date | 2012-08-15
Actual completion date (EV = 100 %) | 2012-10-18
Actual cost overrun | 59000.24 | 11.08%
Sources: BAC and actual final cost from the project's real final report; dates from DSLIB C2014-05.
Status point | Status date | PV | EV | AC | % complete (EV/BAC) | CPI | SPI | EAC A = BAC/CPI | EAC B = AC+(BAC−EV)/(CPI×SPI) | EAC C = AC+(BAC−EV) | Error A vs actual | Error B vs actual | Error C vs actual
Real report 01 May 2012 | 2012-05-01 | 358049.94 | 197506.89 | 249121.29 | 37.1% | 0.79281 | 0.55162 | 671544.8674 | 1014910.9621 | 584024.69 | 13.55% | 71.61% | -1.249%
50 % test point 21 May 2012 (interpolated) | 2012-05-21 | 393063.72 | 266205.14 | 316357.91 | 50% | 0.84147 | 0.67726 | 632715.8319 | 783474.4414 | 582563.06 | 6.984% | 32.48% | -1.496%
Real report 12 Jun 2012 | 2012-06-12 | 432077.21 | 342750.98 | 391275.14 | 64.38% | 0.87598 | 0.79326 | 607785.0186 | 664210.8564 | 580934.45 | 2.769% | 12.31% | -1.771%
How to use: upload Belgium_C2014-05_at_50pct_complete.xlsx in the dashboard, pick each forecasting method in the sidebar, and check that CPI, SPI and EAC match row 12. Then compare EAC with the actual final cost (B4): the error columns show how good each method was.
Error = forecast ÷ actual final cost − 1. Negative = the method under-forecast the final cost.
Rows 11 and 13 are real reports (the app shows them if you upload the full project and pick that reporting date). Row 12 is the interpolated 50 % point and is test data, not a real observation.
Blue = input values taken from the data; black = Excel formulas.