## AI usage log
AI Usage Log — CE 725 Topic 7: EVM Dashboard (format: course guidelines, Annexure A)
Entries 1–37 record the AI-assisted build session (Claude, Anthropic). Each decision must be confirmed by the team (last column). The final row is for genuine team entries (other AI use); add rows as needed. Source file: reports/ai_usage_log.csv.
No. | Date | Tool | Purpose / Prompt Summary | Output Summary | Decision (Accept / Modify / Reject) | Reason and Verification | Needs team confirmation
1 | 2026-10-21 | Claude (Anthropic), Opus 5.5, claude.ai agentic session | Requirements analysis: read course PDF + charter; list mandatory deliverables; build requirements traceability matrix | RTM with 27 requirements (A = professor, B = assumption, C = enhancement); flagged spelling conflict Andhare/Bhadare and missing team number | Accept (pending team review) | Each RTM row cross-checked against the PDF section cited. Name conflict left for team to resolve. | YES — team to confirm decision
2 | 2026-10-21 | Claude (Anthropic), Opus 5.5, claude.ai agentic session | Design the EVM calculation approach and data model | Metric type carrying value + status (ok/review/undefined/not applicable) so undefined indices are never shown as 0; separate engine, forecasting, validation, UI | Accept | Unit tests for AC = 0, PV = 0, EV = 0 confirm undefined values are not numbers (test_evm_calculations.py). | YES — team to confirm decision
3 | 2026-10-21 | Claude (Anthropic), Opus 5.5, claude.ai agentic session | Design benchmark case and solve two periods by hand | 4-WP G+4 residential block, BAC Rs 4 crore, P1 31-Jan-2026, P2 28-Feb-2026, intermediate working for all metrics | Accept (pending team paper check) | Paper working agreed with exact-fraction script and plain-formula workbook. Team must still redo on paper (validation report s.15). | YES — team to confirm decision
4 | 2026-10-21 | Claude (Anthropic), Opus 5.5, claude.ai agentic session | Independent cross-check script for benchmark (exact fractions, no app imports) | benchmark/independent_benchmark_calc.py -> benchmark_expected.csv (54 values) | Accept | Output identical to hand values, e.g. P1 EAC(B) = 46,906,445.3125. Test enforces no app imports. | YES — team to confirm decision
5 | 2026-10-21 | Claude (Anthropic), Opus 5.5, claude.ai agentic session | Plain-formula spreadsheet benchmark | benchmark_workbook.xlsx with 73 formulas, zero-denominator guards | Accept | Recalculated in LibreOffice: 0 formula errors; values match hand calculation. | YES — team to confirm decision
6 | 2026-10-21 | Claude (Anthropic), Opus 5.5, claude.ai agentic session | Generate synthetic demo and benchmark datasets | 9-month, 6-WP G+7 commercial building (BAC Rs 12 crore) in three formats + Excel; benchmark CSV | Accept (labelled SYNTHETIC) | All four files load with no errors; three formats give same results within Rs 0.40. | YES — team to confirm decision
7 | 2026-10-21 | Claude (Anthropic), Opus 5.5, claude.ai agentic session | Write forecasting module (EAC methods A-D, ETC, VAC, overrun, TCPI to BAC and to EAC) | src/forecasting.py with denominator checks and review flags | Accept | Hand-worked tests (BAC 1000, EV 400, AC 500) for every method; TCPI identities (TCPI_EAC(A) = CPI etc.) tested. | YES — team to confirm decision
8 | 2026-10-21 | Claude (Anthropic), Opus 5.5, claude.ai agentic session | Write input validation and data processing for 3 input modes | src/validation.py, src/data_processing.py: blocking errors vs warnings, column mapping, no silent repair | Accept | 36 input-pipeline tests (tests/test_data_validation.py) incl. missing values, negatives, ranges, duplicates, cumulative/period conflicts. | YES — team to confirm decision
9 | 2026-10-21 | Claude (Anthropic), Opus 5.5, claude.ai agentic session | Design question: should MS Project '% Complete' auto-map to physical progress? | AI excluded it from automatic mapping because it is duration-based, not physical | Accept | Test test_unknown_and_duration_percent_columns_not_interpreted. Team should verify the claim about MS Project in its documentation. | YES — team to confirm decision
10 | 2026-10-21 | Claude (Anthropic), Opus 5.5, claude.ai agentic session | Write automated test suite | 71 tests on first run: 70 passed, 1 failed | Modify | Failure was a defect in the AI's own test (text search matched a docstring). Rewritten to inspect import statements; 71/71 passed. (Defect D1) | YES — team to confirm decision
11 | 2026-10-21 | Claude (Anthropic), Opus 5.5, claude.ai agentic session | Check that tests can detect errors (mutation testing) | 7 typical formula errors injected one at a time into a temporary copy | Accept | All 7 detected (1-8 failing tests each). Recorded in validation report s.12. | YES — team to confirm decision
12 | 2026-10-21 | Claude (Anthropic), Opus 5.5, claude.ai agentic session | Build Streamlit dashboard (5 tabs, upload, manual entry, exports) | app.py + src/charts.py, src/formatting.py, src/commentary.py | Accept after fixes (see next entries) | AppTest: app runs with no exceptions; KPI values match pipeline output. | YES — team to confirm decision
13 | 2026-10-21 | Claude (Anthropic), Opus 5.5, claude.ai agentic session | Real-browser test of upload workflow | Found: project name from a rejected upload carried over to the next valid upload | Modify | Root cause: widget state shared between files. Keyed widgets per file; browser retest shows file's own name. (Defect D2) | YES — team to confirm decision
14 | 2026-10-21 | Claude (Anthropic), Opus 5.5, claude.ai agentic session | Review screenshots of the dashboard | Found clipped header, truncated KPI labels, overlapping chart labels, axis cutting off 1.00 line, dates shown with 00:00:00 | Modify | Layout corrected; screenshots regenerated and re-inspected. (Defect D6) | YES — team to confirm decision
15 | 2026-10-21 | Claude (Anthropic), Opus 5.5, claude.ai agentic session | Review validation messages for a faulty file | Found duplicate error for one cell and an internal field name in a warning | Modify | Fixed; faulty upload now shows 5 distinct errors with user column names. (Defects D3, D4) | YES — team to confirm decision
16 | 2026-10-21 | Claude (Anthropic), Opus 5.5, claude.ai agentic session | Rule-based monthly commentary and health screening | Commentary separates facts / changes / forecast / investigations / caveats; never asserts causes; thresholds configurable | Accept (thresholds need team approval) | Output read against the numbers for the demo project; e.g. CPI fell 5 consecutive reports verified from data. Thresholds 1.00/0.90, 0%/10% are team assumptions. | YES — team to confirm decision
17 | 2026-10-21 | Claude (Anthropic), Opus 5.5, claude.ai agentic session | Automate a cell edit in the manual-entry table in the browser | Three scripted attempts did not register in the canvas grid | Reject (automation approach) | Not claimed as verified. Team to check by hand (validation report s.11). | YES — team to confirm decision
18 | 2026-10-21 | Claude (Anthropic), Opus 5.5, claude.ai agentic session | Investigate precision of percentage-based input | Found Rs 0.40 EV difference caused by % stored to 6 decimals | Accept as documented limitation | Recomputed from WP data; listed in assumptions_and_limitations.md. | YES — team to confirm decision
19 | 2026-10-21 | Claude (Anthropic), Opus 5.5, claude.ai agentic session | Check compatibility with older library versions | Clean environment with pandas 2.2.3, Streamlit 1.50, Plotly 5.24 | Accept | 79 tests passed; requirements.txt states both tested combinations. | YES — team to confirm decision
20 | 2026-10-21 | Claude (Anthropic), Opus 5.5, claude.ai agentic session | Draft user manual | First draft rendered to 8 pages | Modify | Screenshots cropped and layout tightened; rendered PDF is 5 pages (course limit 3-5). | YES — team to confirm decision
21 | 2026-10-21 | Claude (Anthropic), Opus 5.5, claude.ai agentic session | Draft validation report from actual test outputs | Report with paper working, 54-row comparison table, defects D1-D6, edge cases, mutation tests, sign-off table | Accept (pending team sign-off) | Tables generated from benchmark/compare_with_dashboard.py output, not typed. | YES — team to confirm decision
22 | 2026-10-21 | Claude (Anthropic), Opus 5.5, claude.ai agentic session | Plan the deliverables and the role split for Topic 7 (prompt: 'tell me how I can deliver things and what we need') | Deliverable list, metric/formula table, role-by-role tasks and a 4-week plan | Accept (as a plan) | Checked against the course guidelines PDF, Section 6; course dates and team roles kept from the charter. | YES — team to confirm decision
23 | 2026-10-21 | Claude (Anthropic), Opus 5.5, claude.ai agentic session | Where can we get real project data? | Suggested the DSLIB empirical database (Ghent University), MoSPI flash reports for Indian context only, textbook cases for formula checks | Accept | DSLIB release located on GitHub; citation Batselier & Vanhoucke (2015) checked. MoSPI kept for the problem statement only (no period data). | YES — team to confirm decision
24 | 2026-10-21 | Claude (Anthropic), Opus 5.5, claude.ai agentic session | Extract the DSLIB data ('pull out that data') | Downloaded DSLIB v3.4 (231 projects); extracted 78 construction projects with authentic tracking data at project and activity level | Accept | AI recomputed CPI/SPI from the extracted PV/EV/AC and compared with ProTrack's own values: all 836 periods agree (difference < 1e-13). | YES — team to confirm decision
25 | 2026-10-23 | Claude (Anthropic), Opus 5.5, claude.ai agentic session | One real project with activity-level data to test the dashboard | Apartment Building (4) workbook: 39 activities, 13 reports, answer-key sheets | Modify | AI rounded % complete to 4 decimals, which created false variances of up to EUR 3.88; caught by the AI's own test against ProTrack; corrected to full precision. | YES — team to confirm decision
26 | 2026-10-27 | Claude (Anthropic), Opus 5.5, claude.ai agentic session | Make the requested UI changes (home screen, combined chart, work-package analysis) | AI first built a NEW separate app instead of changing the team's app on GitHub | Reject | Team pointed out the error. Changes were then made in the team repository (pull request #1) with tests; the separate app was discarded. | YES — team to confirm decision
27 | 2026-10-27 | Claude (Anthropic), Opus 5.5, claude.ai agentic session | Work-package status and top problem activities (mock-up and code) | Mock-up showed a work package with CPI 0.86 as 'Amber' and ranked two equal-looking activities from rounded values | Modify | Both were AI errors: the team's rule makes CPI < 0.90 'Critical'; the true values differ by EUR 0.25. Caught by tests written from hand-calculated values. | YES — team to confirm decision
28 | 2026-10-27 | Claude (Anthropic), Opus 5.5, claude.ai agentic session | Add AI to the app so uploaded CSV/Excel files are understood | AI offered three options: real AI via the Claude API (paid key, data sent outside), a built-in rule-based reader, or both | Accept (team chose the built-in reader) | Team decision: no API key and no project data leaving the app (confidentiality, Section 6 of the reflection). Rule-based reader is testable and free. | YES — team to confirm decision
29 | 2026-10-27 | Claude (Anthropic), Opus 5.5, claude.ai agentic session | Smart reader for the team's own site sheet (data_63.xlsx) | src/smart_reader.py: header on row 4, status date from cell B1, fractions to %, totals row removed, missing AC reported | Accept (pull request #2) | 38 tests incl. the team's sheet; BAC and PV equal the sheet's own totals; 10/10 injected faults detected; browser test 13/13. | YES — team to confirm decision
30 | 2026-10-27 | Claude (Anthropic), Opus 5.5, claude.ai agentic session | Why does the upload show 'PV looks like PV/EV… not needed'? (Prashant's sheet) | AI explained its own message design was alarming; replaced it with a row-by-row cross-check of supplied PV/EV | Modify (pull request #3) | All 12 activities match; mismatching rows are named with both values; 3/3 injected faults detected. | YES — team to confirm decision
31 | 2026-10-27 | Claude (Anthropic), Opus 5.5, claude.ai agentic session | Why are graphs not generated after upload? | Explained: the file has a single status date (one snapshot), so a trend has one point; proposed two fixes | Accept | Explanation verified on the file. Implemented on 29-Oct: one axis label per date and an explicit note (tests/test_charts.py). | YES — team to confirm decision
32 | 2026-10-27 | Claude (Anthropic), Opus 5.5, claude.ai agentic session | Create a 50 %-complete file to test forecasting | Real Belgian project (DSLIB C2014-05) cut at 50 % with an interpolated report, plus an answer key | Accept with caveat | No real report fell at 50 %; the interpolated rows are labelled in every row and in the answer key. Forecast errors computed against the real final cost. | YES — team to confirm decision
33 | 2026-10-29 | Claude (Anthropic), Opus 5.5, claude.ai agentic session | Real-data case small enough to check by hand, showing every feature | Manual check case: DSLIB C2015-33 grouped into 4 work packages, 5 reports; hand-calculation workbook (502 Excel formulas) | Accept | Workbook = dashboard for 90/90 values; data within the proven rounding bound of ProTrack's values; tests/test_manual_check_case.py. | YES — team to confirm decision
34 | 2026-10-29 | Claude (Anthropic), Opus 5.5, claude.ai agentic session | Summarise the manual check case | Summary table gave CPI at 31-Dec-2013 as 0.714 | Modify | AI rounding slip: 111,728.57 / 156,594.45 = 0.71349 -> 0.713. Caught by an interface test; documents corrected. | YES — team to confirm decision
35 | 2026-10-29 | Claude (Anthropic), Opus 5.5, claude.ai agentic session | Test that the 4-work-package file matches ProTrack | First test used a guessed EUR 3 tolerance | Modify | Observed difference EUR 3.79. Tolerance replaced by the derived bound 0.005 % x BAC = EUR 10.72. | YES — team to confirm decision
36 | 2026-10-29 | Claude (Anthropic), Opus 5.5, claude.ai agentic session | Improve user experience: visible Home button, premium look, better graphs | Top control bar (Home, reporting date, method), refined banner/cards, coloured CPI/SPI zones, one label per date | Modify | Screenshot review found the AI's CSS targeted an element that does not exist in Streamlit 1.66 and table columns pushed off-screen; both corrected. 161 tests; 6/6 injected faults detected. | YES — team to confirm decision
37 | 2026-10-29 | Claude (Anthropic), Opus 5.5, claude.ai agentic session | Update the deliverables (user manual, validation report, reflection draft, viva bank, slides) | Updated documents from the actual runs; reflection draft expanded; individual reflections left for members | Accept (pending team review) | User manual rendered to 5 pages; validation report Part B generated by benchmark/compare_manual_check_case.py; personal sections not written by the AI. | YES — team to confirm decision
38 | [team to fill] | [team to fill] | [Earlier team AI use, e.g. topic selection / charter drafting / literature search — add genuine entries only] |  |  |  | TEAM ENTRY

## Summary
Decision | Entries
Accept | 24
Modify | 11
Reject | 2
Total | 37
Counts use the Decision column; the team-entry row is not counted until it is filled.