## Read me
Manual check case: IJzertoren Memorial Square (real project)
Real project from the DSLIB database (Ghent University): Batselier, J. & Vanhoucke, M. (2015), International Journal of Project Management 33(3), 697-710. Project C2015-33, Belgium, 2013-14, EUR.
Baseline 14-Oct-2013 to 20-Dec-2013; 5 month-end progress reports; finished on 28-Feb-2014, about 2 months late and 4.8 % over budget.
The 12 real activities are grouped into 4 work packages. Budgets, PV and EV are sums of the activity values recorded in ProTrack; % values are rounded to 2 decimals so everything can be checked with a calculator.
Sheets
Inputs - the 20 input rows (5 dates x 4 work packages), identical to the upload file C2015-33_ijzertoren_manual_check_work_packages.csv. Blue = typed input.
Work package calculation - PV, EV, AC, CV, SV, CPI, SPI and status for every work package and date.
Project calculation - every dashboard metric for every date: CPI, SPI, EAC (A, B, C), ETC, VAC, TCPI, health. Rows 3 and 4 (30-Nov and 31-Dec) are the two benchmark periods worked by hand in the validation report.
Forecast check - each forecast compared with the real final cost (known because the project is complete).
Feature tour - which dashboard feature to show at which date, using this data.
Settings - health thresholds (same defaults as the dashboard sidebar) and an example for method D.
How to check the app: upload the CSV (or press 'Manual check case' on the dashboard home screen), pick a reporting date in the sidebar, and compare each figure with the same row here. All cells in black are formulas - click any cell to see how it is calculated.

## Inputs
Period | Reporting date | WP ID | Work package | Budget | Planned progress % | Actual progress % | AC cumulative
1 | 2013-10-31 | WP1 | Demolition and sewerage | 49231.67 | 100 | 61.54 | 28328.72
1 | 2013-10-31 | WP2 | Earthworks and foundations | 58025.66 | 20.67 | 5.17 | 995.46
1 | 2013-10-31 | WP3 | Kerbs, paving and concrete | 78356.7 | 0 | 0 | 0
1 | 2013-10-31 | WP4 | Finishing: street furniture and signage | 28803.68 | 0 | 0 | 0
2 | 2013-11-30 | WP1 | Demolition and sewerage | 49231.67 | 100 | 92.31 | 38459.62
2 | 2013-11-30 | WP2 | Earthworks and foundations | 58025.66 | 100 | 32.64 | 50759.94
2 | 2013-11-30 | WP3 | Kerbs, paving and concrete | 78356.7 | 5.75 | 12.4 | 10271.32
2 | 2013-11-30 | WP4 | Finishing: street furniture and signage | 28803.68 | 0 | 19.74 | 6201.39
3 | 2013-12-31 | WP1 | Demolition and sewerage | 49231.67 | 100 | 100 | 39821.67
3 | 2013-12-31 | WP2 | Earthworks and foundations | 58025.66 | 100 | 58.03 | 69412.98
3 | 2013-12-31 | WP3 | Kerbs, paving and concrete | 78356.7 | 100 | 22.27 | 40197.69
3 | 2013-12-31 | WP4 | Finishing: street furniture and signage | 28803.68 | 100 | 39.49 | 7162.11
4 | 2014-01-31 | WP1 | Demolition and sewerage | 49231.67 | 100 | 100 | 41243.3
4 | 2014-01-31 | WP2 | Earthworks and foundations | 58025.66 | 100 | 86.78 | 71306.63
4 | 2014-01-31 | WP3 | Kerbs, paving and concrete | 78356.7 | 100 | 94.36 | 72729.71
4 | 2014-01-31 | WP4 | Finishing: street furniture and signage | 28803.68 | 100 | 59.23 | 9479.96
5 | 2014-02-28 | WP1 | Demolition and sewerage | 49231.67 | 100 | 100 | 41595.68
5 | 2014-02-28 | WP2 | Earthworks and foundations | 58025.66 | 100 | 100 | 80867.4
5 | 2014-02-28 | WP3 | Kerbs, paving and concrete | 78356.7 | 100 | 100 | 75546.95
5 | 2014-02-28 | WP4 | Finishing: street furniture and signage | 28803.68 | 100 | 100 | 26779.64

## Work package calculation
Period | Status date | WP ID | Work package | Budget | Planned % | Actual % | PV | EV | AC | CV | SV | CPI | SPI | Status
1 | 2013-10-31 | WP1 | Demolition and sewerage | 49231.67 | 100 | 61.54 | 49231.67 | 30297.1697 | 28328.72 | 1968.4497 | -18934.5003 | 1.0695 | 0.6154 | Critical
1 | 2013-10-31 | WP2 | Earthworks and foundations | 58025.66 | 20.67 | 5.17 | 11993.9039 | 2999.9266 | 995.46 | 2004.4666 | -8993.9773 | 3.0136 | 0.25012 | Critical
1 | 2013-10-31 | WP3 | Kerbs, paving and concrete | 78356.7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Undefined | Undefined | Not started
1 | 2013-10-31 | WP4 | Finishing: street furniture and signage | 28803.68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Undefined | Undefined | Not started
2 | 2013-11-30 | WP1 | Demolition and sewerage | 49231.67 | 100 | 92.31 | 49231.67 | 45445.7546 | 38459.62 | 6986.1346 | -3785.9154 | 1.1816 | 0.9231 | Warning
2 | 2013-11-30 | WP2 | Earthworks and foundations | 58025.66 | 100 | 32.64 | 58025.66 | 18939.5754 | 50759.94 | -31820.3646 | -39086.0846 | 0.37312 | 0.3264 | Critical
2 | 2013-11-30 | WP3 | Kerbs, paving and concrete | 78356.7 | 5.75 | 12.4 | 4505.5103 | 9716.2308 | 10271.32 | -555.0892 | 5210.7206 | 0.94596 | 2.1565 | Warning
2 | 2013-11-30 | WP4 | Finishing: street furniture and signage | 28803.68 | 0 | 19.74 | 0 | 5685.8464 | 6201.39 | -515.5436 | 5685.8464 | 0.91687 | Undefined | Insufficient data
3 | 2013-12-31 | WP1 | Demolition and sewerage | 49231.67 | 100 | 100 | 49231.67 | 49231.67 | 39821.67 | 9410 | 0 | 1.2363 | 1 | Favourable
3 | 2013-12-31 | WP2 | Earthworks and foundations | 58025.66 | 100 | 58.03 | 58025.66 | 33672.2905 | 69412.98 | -35740.6895 | -24353.3695 | 0.4851 | 0.5803 | Critical
3 | 2013-12-31 | WP3 | Kerbs, paving and concrete | 78356.7 | 100 | 22.27 | 78356.7 | 17450.0371 | 40197.69 | -22747.6529 | -60906.6629 | 0.43411 | 0.2227 | Critical
3 | 2013-12-31 | WP4 | Finishing: street furniture and signage | 28803.68 | 100 | 39.49 | 28803.68 | 11374.5732 | 7162.11 | 4212.4632 | -17429.1068 | 1.5882 | 0.3949 | Critical
4 | 2014-01-31 | WP1 | Demolition and sewerage | 49231.67 | 100 | 100 | 49231.67 | 49231.67 | 41243.3 | 7988.37 | 0 | 1.1937 | 1 | Favourable
4 | 2014-01-31 | WP2 | Earthworks and foundations | 58025.66 | 100 | 86.78 | 58025.66 | 50354.6677 | 71306.63 | -20951.9623 | -7670.9923 | 0.70617 | 0.8678 | Critical
4 | 2014-01-31 | WP3 | Kerbs, paving and concrete | 78356.7 | 100 | 94.36 | 78356.7 | 73937.3821 | 72729.71 | 1207.6721 | -4419.3179 | 1.0166 | 0.9436 | Warning
4 | 2014-01-31 | WP4 | Finishing: street furniture and signage | 28803.68 | 100 | 59.23 | 28803.68 | 17060.4197 | 9479.96 | 7580.4597 | -11743.2603 | 1.7996 | 0.5923 | Critical
5 | 2014-02-28 | WP1 | Demolition and sewerage | 49231.67 | 100 | 100 | 49231.67 | 49231.67 | 41595.68 | 7635.99 | 0 | 1.1836 | 1 | Favourable
5 | 2014-02-28 | WP2 | Earthworks and foundations | 58025.66 | 100 | 100 | 58025.66 | 58025.66 | 80867.4 | -22841.74 | 0 | 0.71754 | 1 | Critical
5 | 2014-02-28 | WP3 | Kerbs, paving and concrete | 78356.7 | 100 | 100 | 78356.7 | 78356.7 | 75546.95 | 2809.75 | 0 | 1.0372 | 1 | Favourable
5 | 2014-02-28 | WP4 | Finishing: street furniture and signage | 28803.68 | 100 | 100 | 28803.68 | 28803.68 | 26779.64 | 2024.04 | 0 | 1.0756 | 1 | Favourable

## Project calculation
Period | Status date | BAC | PV | EV | AC | CV | SV | CPI | SPI | % planned | % complete | % spent | EAC A | EAC B | EAC C | ETC A | ETC B | ETC C | VAC A | VAC B | VAC C | Overrun % A | TCPI to BAC | TCPI to EAC A | TCPI to EAC B | TCPI to EAC C | CPI status | SPI status | Overrun status (A) | Overall health (method A)
1 | 2013-10-31 | 214417.71 | 61225.5739 | 33297.0963 | 29324.18 | 3972.9163 | -27928.4776 | 1.1355 | 0.54384 | 28.5543 | 15.5291 | 13.6762 | 188833.989 | 322625.4187 | 210444.7937 | 159509.809 | 293301.2387 | 181120.6137 | 25583.721 | -108207.7087 | 3972.9163 | -11.9317 | 0.97854 | 1.1355 | 0.61752 | 1 | Favourable | Critical | Favourable | Critical
2 | 2013-11-30 | 214417.71 | 111762.8402 | 79787.4072 | 105692.27 | -25904.8628 | -31975.433 | 0.7549 | 0.7139 | 52.1239 | 37.2112 | 49.2927 | 284033.4745 | 355505.1194 | 240322.5728 | 178341.2045 | 249812.8494 | 134630.3028 | -69615.7645 | -141087.4094 | -25904.8628 | 32.4674 | 1.2383 | 0.7549 | 0.53892 | 1 | Critical | Critical | Critical | Critical
3 | 2013-12-31 | 214417.71 | 214417.71 | 111728.5708 | 156594.45 | -44865.8792 | -102689.1392 | 0.71349 | 0.52108 | 100 | 52.1079 | 73.0324 | 300519.5817 | 432800.4099 | 259283.5892 | 143925.1317 | 276205.9599 | 102689.1392 | -86101.8717 | -218382.6999 | -44865.8792 | 40.1561 | 1.7759 | 0.71349 | 0.37178 | 1 | Critical | Critical | Critical | Critical
4 | 2014-01-31 | 214417.71 | 214417.71 | 190584.1395 | 194759.6 | -4175.4605 | -23833.5705 | 0.97856 | 0.88885 | 100 | 88.8845 | 90.8319 | 219115.3342 | 222161.1496 | 218593.1705 | 24355.7342 | 27401.5496 | 23833.5705 | -4697.6242 | -7743.4396 | -4175.4605 | 2.1909 | 1.2124 | 0.97856 | 0.86979 | 1 | Warning | Critical | Warning | Critical
5 | 2014-02-28 | 214417.71 | 214417.71 | 214417.71 | 224789.67 | -10371.96 | 0 | 0.95386 | 1 | 100 | 100 | 104.8373 | 224789.67 | 224789.67 | 224789.67 | 0 | 0 | 0 | -10371.96 | -10371.96 | -10371.96 | 4.8373 | N/A | N/A | N/A | N/A | Warning | Favourable | Warning | Warning
Formulas:
Status date = INDEX('Work package calculation'!$B2:B21,MATCH([Period],'Work package calculation'!$A2:A21,0))

## Forecast check
Period | Status date | % complete | EAC A | EAC B | EAC C | Actual final cost | Error A | Error B | Error C
1 | 2013-10-31 | 15.5291 | 188833.989 | 322625.4187 | 210444.7937 | 224789.67 | -16% | 43.52% | -6.381%
2 | 2013-11-30 | 37.2112 | 284033.4745 | 355505.1194 | 240322.5728 | 224789.67 | 26.36% | 58.15% | 6.91%
3 | 2013-12-31 | 52.1079 | 300519.5817 | 432800.4099 | 259283.5892 | 224789.67 | 33.69% | 92.54% | 15.34%
4 | 2014-01-31 | 88.8845 | 219115.3342 | 222161.1496 | 218593.1705 | 224789.67 | -2.524% | -1.169% | -2.757%
5 | 2014-02-28 | 100 | 224789.67 | 224789.67 | 224789.67 | 224789.67 | 0% | 0% | 0%
Error = forecast / actual final cost - 1. Negative = the method under-forecast the final cost. Read row 4 (31-Dec-2013, about 52 % complete) as 'what would we have predicted half way?'

## Feature tour
Feature | Reporting date to select | What to show / explain
Home screen and upload | - | Upload the CSV, or press 'Manual check case' on the home screen. The smart reader shows the data type it detected and the column matches.
Signboard and KPI cards | 31 Oct 2013 | CPI 1.135 (cost favourable) but SPI 0.544 (behind schedule) -> Critical.
Not started / early start | 31 Oct 2013 and 30 Nov 2013 | 31 Oct: WP3 and WP4 'Not started'. 30 Nov: WP4 has progress before any work was planned (PV = 0), so its SPI is undefined -> 'Insufficient data' (never shown as 0).
Top problem activities | 30 Nov 2013 | WP2 Earthworks and foundations: AC far above EV (CPI about 0.37).
CPI and SPI trend (combined chart) | 28 Feb 2014 | CPI falls from 1.14 to 0.71 and recovers to 0.95; SPI recovers to 1.00 at completion although the project was 2 months late (SPI limitation).
S-curve | any | PV reaches BAC on 20 Dec 2013 (baseline finish); EV and AC continue to 28 Feb 2014.
Forecasts A, B, C | 31 Dec 2013 | Half way (52 % complete): compare EAC A, B, C with the real final cost EUR 224,789.67 (sheet 'Forecast check').
Method D (independent ETC) | 31 Dec 2013 | Forecasts tab: enter an ETC; the EAC equals AC + ETC (Settings B8).
TCPI | 31 Dec 2013 and 28 Feb 2014 | 31 Dec: efficiency needed to finish on budget. 28 Feb: EV = BAC, so TCPI does not apply (shown as N/A).
Health thresholds | any | Change 'CPI/SPI critical below' in the sidebar and in Settings B3: both update.
Commentary and exports | any | Commentary tab text; Data tab downloads (CSV, Excel workbook).

## Settings
Setting | Value | Note
CPI/SPI warning below | 1 | Dashboard default (sidebar: Health screening thresholds)
CPI/SPI critical below | 0.9 | Dashboard default
Forecast overrun warning above (%) | 0 | Dashboard default
Forecast overrun critical above (%) | 10 | Dashboard default
Actual final cost (AC at completion, 28-Feb-2014) | 224789.67 | Known only because the project is finished; used in 'Forecast check'
Method D: independent ETC you want to test (enter a number) |  | Example: type a bottom-up estimate of the remaining cost at 31-Dec-2013
Method D: EAC = AC (31-Dec-2013) + independent ETC | Enter an ETC in B7 | Compare with the dashboard: Forecasts tab > Independent estimate, date 31 Dec 2013