## Benchmark
CE 725 EVM Dashboard — Manual benchmark (plain spreadsheet, no macros, no app code)
Illustrative G+4 RCC residential block. SYNTHETIC data for validation only. Blue cells on yellow = inputs; black = formulas. Money in INR. Percentages are cumulative.
1. Inputs (approved budget, cumulative progress, cumulative actual cost)
Work package | Budget (INR) | P1 planned % | P1 actual % | P1 cum. AC (INR) | P2 planned % | P2 actual % | P2 cum. AC (INR)
WP1 Substructure | 8000000 | 100% | 100% | 8400000 | 100% | 100% | 8400000
WP2 RCC superstructure | 16000000 | 40% | 30% | 5200000 | 70% | 55% | 9800000
WP3 Masonry and finishes | 12000000 | 0% | 0% | 0 | 10% | 5% | 700000
WP4 MEP services | 4000000 | 5% | 0% | 100000 | 10% | 5% | 300000
BAC = total budget | 40000000
Reporting dates: P1 = 31-Jan-2026, P2 = 28-Feb-2026
2. Budget-weighted PV and EV per work package (PV_i = Budget_i x planned %, EV_i = Budget_i x actual %)
Work package | P1 PV_i | P1 EV_i | P2 PV_i | P2 EV_i
WP1 Substructure | 8000000 | 8000000 | 8000000 | 8000000
WP2 RCC superstructure | 6400000 | 4800000 | 11200000 | 8800000
WP3 Masonry and finishes | 0 | 0 | 1200000 | 600000
WP4 MEP services | 200000 | 0 | 400000 | 200000
Total | 14600000 | 12800000 | 20800000 | 17600000
3. EVM results (cumulative to each reporting date)
Metric | Formula | Period 1 | Period 2
BAC | Sum of budgets | 40000000 | 40000000
PV | Sum of PV_i | 14600000 | 20800000
EV | Sum of EV_i | 12800000 | 17600000
AC | Sum of cumulative AC_i | 13700000 | 19200000
CV | EV - AC | -900000 | -1600000
SV | EV - PV | -1800000 | -3200000
CPI | EV / AC | 0.93431 | 0.91667
SPI | EV / PV | 0.87671 | 0.84615
EAC (A) BAC/CPI | BAC / CPI | 42812500 | 43636363.6364
EAC (B) CPI x SPI | AC + (BAC-EV)/(CPI x SPI) | 46906445.3125 | 48079338.843
EAC (C) budget rate | AC + (BAC - EV) | 40900000 | 41600000
ETC (A) | EAC(A) - AC | 29112500 | 24436363.6364
ETC (B) | EAC(B) - AC | 33206445.3125 | 28879338.843
ETC (C) | EAC(C) - AC | 27200000 | 22400000
VAC (A) | BAC - EAC(A) | -2812500 | -3636363.6364
VAC (B) | BAC - EAC(B) | -6906445.3125 | -8079338.843
VAC (C) | BAC - EAC(C) | -900000 | -1600000
Overrun % (A) | (EAC(A) - BAC)/BAC x 100 | 7.0312 | 9.0909
Overrun % (B) | (EAC(B) - BAC)/BAC x 100 | 17.2661 | 20.1983
Overrun % (C) | (EAC(C) - BAC)/BAC x 100 | 2.25 | 4
TCPI to BAC | (BAC - EV)/(BAC - AC) | 1.0342 | 1.0769
TCPI to EAC (A) | (BAC - EV)/(EAC(A) - AC) | 0.93431 | 0.91667
TCPI to EAC (B) | (BAC - EV)/(EAC(B) - AC) | 0.81912 | 0.77564
TCPI to EAC (C) | (BAC - EV)/(EAC(C) - AC) | 1 | 1
Prepared as the course's 'plain spreadsheet' benchmark. It does not call or import the dashboard code. The Validation Engineer should independently re-work Period 1 and Period 2 on paper and initial below.
Checked by (name / date / signature):
Note on B6: Synthetic illustrative budget chosen for the benchmark (team assumption).