## Progress-based
project_name | reporting_date | planned_progress_pct | actual_progress_pct | ac_cumulative | bac | notes
Demo - G+7 commercial building (SYNTHETIC) | 2026-01-31 | 5 | 4.375 | 5812000 | 120000000
Demo - G+7 commercial building (SYNTHETIC) | 2026-02-28 | 13.75 | 12.375 | 15712000 | 120000000
Demo - G+7 commercial building (SYNTHETIC) | 2026-03-31 | 21.875 | 19.375 | 24316000 | 120000000
Demo - G+7 commercial building (SYNTHETIC) | 2026-04-30 | 27.5 | 24.875 | 31130000 | 120000000
Demo - G+7 commercial building (SYNTHETIC) | 2026-05-31 | 35.125 | 30.75 | 38648000 | 120000000 | MEP procurement advance paid before site progress
Demo - G+7 commercial building (SYNTHETIC) | 2026-06-30 | 45.875 | 39.5833 | 49853000 | 120000000
Demo - G+7 commercial building (SYNTHETIC) | 2026-07-31 | 56.625 | 48.5833 | 61331000 | 120000000
Demo - G+7 commercial building (SYNTHETIC) | 2026-08-31 | 68.875 | 58.5417 | 74033000 | 120000000 | Reinforcement steel price increase reported by site
Demo - G+7 commercial building (SYNTHETIC) | 2026-09-30 | 76.25 | 68.375 | 86602000 | 120000000

## Pre-calculated EVM
project_name | reporting_date | bac | pv_cumulative | ev_cumulative | ac_cumulative | notes
Demo - G+7 commercial building (SYNTHETIC) | 2026-01-31 | 120000000 | 6000000 | 5250000 | 5812000
Demo - G+7 commercial building (SYNTHETIC) | 2026-02-28 | 120000000 | 16500000 | 14850000 | 15712000
Demo - G+7 commercial building (SYNTHETIC) | 2026-03-31 | 120000000 | 26250000 | 23250000 | 24316000
Demo - G+7 commercial building (SYNTHETIC) | 2026-04-30 | 120000000 | 33000000 | 29850000 | 31130000
Demo - G+7 commercial building (SYNTHETIC) | 2026-05-31 | 120000000 | 42150000 | 36900000 | 38648000 | MEP procurement advance paid before site progress
Demo - G+7 commercial building (SYNTHETIC) | 2026-06-30 | 120000000 | 55050000 | 47500000 | 49853000
Demo - G+7 commercial building (SYNTHETIC) | 2026-07-31 | 120000000 | 67950000 | 58300000 | 61331000
Demo - G+7 commercial building (SYNTHETIC) | 2026-08-31 | 120000000 | 82650000 | 70250000 | 74033000 | Reinforcement steel price increase reported by site
Demo - G+7 commercial building (SYNTHETIC) | 2026-09-30 | 120000000 | 91500000 | 82050000 | 86602000

## Work packages
project_name | reporting_date | activity_id | activity_name | activity_budget | planned_progress_pct | actual_progress_pct | ac_cumulative | notes
Demo - G+7 commercial building (SYNTHETIC) | 2026-01-31 | WP1 | Site preparation and substructure | 15000000 | 40 | 35 | 5812000
Demo - G+7 commercial building (SYNTHETIC) | 2026-01-31 | WP2 | RCC frame and slabs | 45000000 | 0 | 0 | 0
Demo - G+7 commercial building (SYNTHETIC) | 2026-01-31 | WP3 | Masonry and plastering | 12000000 | 0 | 0 | 0
Demo - G+7 commercial building (SYNTHETIC) | 2026-01-31 | WP4 | MEP services | 25000000 | 0 | 0 | 0
Demo - G+7 commercial building (SYNTHETIC) | 2026-01-31 | WP5 | Finishes and facade | 18000000 | 0 | 0 | 0
Demo - G+7 commercial building (SYNTHETIC) | 2026-01-31 | WP6 | External works | 5000000 | 0 | 0 | 0
Demo - G+7 commercial building (SYNTHETIC) | 2026-02-28 | WP1 | Site preparation and substructure | 15000000 | 80 | 75 | 12112000
Demo - G+7 commercial building (SYNTHETIC) | 2026-02-28 | WP2 | RCC frame and slabs | 45000000 | 10 | 8 | 3600000
Demo - G+7 commercial building (SYNTHETIC) | 2026-02-28 | WP3 | Masonry and plastering | 12000000 | 0 | 0 | 0
Demo - G+7 commercial building (SYNTHETIC) | 2026-02-28 | WP4 | MEP services | 25000000 | 0 | 0 | 0
Demo - G+7 commercial building (SYNTHETIC) | 2026-02-28 | WP5 | Finishes and facade | 18000000 | 0 | 0 | 0
Demo - G+7 commercial building (SYNTHETIC) | 2026-02-28 | WP6 | External works | 5000000 | 0 | 0 | 0
Demo - G+7 commercial building (SYNTHETIC) | 2026-03-31 | WP1 | Site preparation and substructure | 15000000 | 100 | 95 | 15262000
Demo - G+7 commercial building (SYNTHETIC) | 2026-03-31 | WP2 | RCC frame and slabs | 45000000 | 25 | 20 | 9054000
Demo - G+7 commercial building (SYNTHETIC) | 2026-03-31 | WP3 | Masonry and plastering | 12000000 | 0 | 0 | 0
Demo - G+7 commercial building (SYNTHETIC) | 2026-03-31 | WP4 | MEP services | 25000000 | 0 | 0 | 0
Demo - G+7 commercial building (SYNTHETIC) | 2026-03-31 | WP5 | Finishes and facade | 18000000 | 0 | 0 | 0
Demo - G+7 commercial building (SYNTHETIC) | 2026-03-31 | WP6 | External works | 5000000 | 0 | 0 | 0
Demo - G+7 commercial building (SYNTHETIC) | 2026-04-30 | WP1 | Site preparation and substructure | 15000000 | 100 | 100 | 16050000
Demo - G+7 commercial building (SYNTHETIC) | 2026-04-30 | WP2 | RCC frame and slabs | 45000000 | 40 | 33 | 15080000
Demo - G+7 commercial building (SYNTHETIC) | 2026-04-30 | WP3 | Masonry and plastering | 12000000 | 0 | 0 | 0
Demo - G+7 commercial building (SYNTHETIC) | 2026-04-30 | WP4 | MEP services | 25000000 | 0 | 0 | 0
Demo - G+7 commercial building (SYNTHETIC) | 2026-04-30 | WP5 | Finishes and facade | 18000000 | 0 | 0 | 0
Demo - G+7 commercial building (SYNTHETIC) | 2026-04-30 | WP6 | External works | 5000000 | 0 | 0 | 0
Demo - G+7 commercial building (SYNTHETIC) | 2026-05-31 | WP1 | Site preparation and substructure | 15000000 | 100 | 100 | 16050000
Demo - G+7 commercial building (SYNTHETIC) | 2026-05-31 | WP2 | RCC frame and slabs | 45000000 | 55 | 46 | 21222000
Demo - G+7 commercial building (SYNTHETIC) | 2026-05-31 | WP3 | Masonry and plastering | 12000000 | 20 | 10 | 1176000
Demo - G+7 commercial building (SYNTHETIC) | 2026-05-31 | WP4 | MEP services | 25000000 | 0 | 0 | 200000
Demo - G+7 commercial building (SYNTHETIC) | 2026-05-31 | WP5 | Finishes and facade | 18000000 | 0 | 0 | 0
Demo - G+7 commercial building (SYNTHETIC) | 2026-05-31 | WP6 | External works | 5000000 | 0 | 0 | 0
Demo - G+7 commercial building (SYNTHETIC) | 2026-06-30 | WP1 | Site preparation and substructure | 15000000 | 100 | 100 | 16050000
Demo - G+7 commercial building (SYNTHETIC) | 2026-06-30 | WP2 | RCC frame and slabs | 45000000 | 70 | 60 | 27963000
Demo - G+7 commercial building (SYNTHETIC) | 2026-06-30 | WP3 | Masonry and plastering | 12000000 | 40 | 25 | 2940000
Demo - G+7 commercial building (SYNTHETIC) | 2026-06-30 | WP4 | MEP services | 25000000 | 15 | 10 | 2900000
Demo - G+7 commercial building (SYNTHETIC) | 2026-06-30 | WP5 | Finishes and facade | 18000000 | 0 | 0 | 0
Demo - G+7 commercial building (SYNTHETIC) | 2026-06-30 | WP6 | External works | 5000000 | 0 | 0 | 0
Demo - G+7 commercial building (SYNTHETIC) | 2026-07-31 | WP1 | Site preparation and substructure | 15000000 | 100 | 100 | 16050000
Demo - G+7 commercial building (SYNTHETIC) | 2026-07-31 | WP2 | RCC frame and slabs | 45000000 | 85 | 72 | 33849000
Demo - G+7 commercial building (SYNTHETIC) | 2026-07-31 | WP3 | Masonry and plastering | 12000000 | 60 | 45 | 5292000
Demo - G+7 commercial building (SYNTHETIC) | 2026-07-31 | WP4 | MEP services | 25000000 | 30 | 22 | 6140000
Demo - G+7 commercial building (SYNTHETIC) | 2026-07-31 | WP5 | Finishes and facade | 18000000 | 0 | 0 | 0
Demo - G+7 commercial building (SYNTHETIC) | 2026-07-31 | WP6 | External works | 5000000 | 0 | 0 | 0
Demo - G+7 commercial building (SYNTHETIC) | 2026-08-31 | WP1 | Site preparation and substructure | 15000000 | 100 | 100 | 16050000
Demo - G+7 commercial building (SYNTHETIC) | 2026-08-31 | WP2 | RCC frame and slabs | 45000000 | 100 | 84 | 39789000
Demo - G+7 commercial building (SYNTHETIC) | 2026-08-31 | WP3 | Masonry and plastering | 12000000 | 80 | 65 | 7644000
Demo - G+7 commercial building (SYNTHETIC) | 2026-08-31 | WP4 | MEP services | 25000000 | 45 | 35 | 9650000
Demo - G+7 commercial building (SYNTHETIC) | 2026-08-31 | WP5 | Finishes and facade | 18000000 | 10 | 5 | 900000
Demo - G+7 commercial building (SYNTHETIC) | 2026-08-31 | WP6 | External works | 5000000 | 0 | 0 | 0
Demo - G+7 commercial building (SYNTHETIC) | 2026-09-30 | WP1 | Site preparation and substructure | 15000000 | 100 | 100 | 16050000
Demo - G+7 commercial building (SYNTHETIC) | 2026-09-30 | WP2 | RCC frame and slabs | 45000000 | 100 | 95 | 45284000
Demo - G+7 commercial building (SYNTHETIC) | 2026-09-30 | WP3 | Masonry and plastering | 12000000 | 100 | 80 | 9408000
Demo - G+7 commercial building (SYNTHETIC) | 2026-09-30 | WP4 | MEP services | 25000000 | 60 | 48 | 13160000
Demo - G+7 commercial building (SYNTHETIC) | 2026-09-30 | WP5 | Finishes and facade | 18000000 | 25 | 15 | 2700000
Demo - G+7 commercial building (SYNTHETIC) | 2026-09-30 | WP6 | External works | 5000000 | 0 | 0 | 0