# EVM Dashboard — Validation Report

CE 725 Construction Economics and Finance · Course project, Topic 7

Status of this report. All test results below come from actual runs on 21-Oct-2026 (evidence: reports/test_results.txt, reports/benchmark_comparison.md, reports/browser_test_log.txt). The independent benchmark calculations were prepared with AI assistance (Claude) separately from the dashboard code. The course requires the team to verify every number against a manual benchmark; the Validation Engineer must redo Section 4 on paper and sign Section 15 before submission. Until then, Section 4 is “prepared, awaiting team verification”.

# 1. Validation objective

To show that every metric the dashboard reports — PV, EV, AC, CV, SV, CPI, SPI, EAC (methods A–C), ETC, VAC, forecast overrun, TCPI to BAC and TCPI to EAC — equals an independently prepared manual result for two reporting periods (course requirement, Topic 7), and that undefined, invalid and edge-case inputs are handled without displaying fabricated numbers.

# 2. Benchmark project

Synthetic, illustrative G+4 RCC residential block. Four work packages; BAC ₹4,00,00,000 (sum of WP budgets). Two monthly status dates: Period 1 = 31-Jan-2026, Period 2 = 28-Feb-2026. A work-package case was chosen deliberately because it also tests budget weighting, the most common EV error. It also contains cost without progress (WP4, Period 1: ₹1,00,000 spent at 0% complete — a procurement advance), which must not be treated as an error.

# 3. Input data (cumulative)

| Work package | Budget (₹) | P1 planned % | P1 actual % | P1 AC (₹) | P2 planned % | P2 actual % | P2 AC (₹) |
| --- | --- | --- | --- | --- | --- | --- | --- |
| WP1 Substructure | 80,00,000 | 100 | 100 | 84,00,000 | 100 | 100 | 84,00,000 |
| WP2 RCC superstructure | 1,60,00,000 | 40 | 30 | 52,00,000 | 70 | 55 | 98,00,000 |
| WP3 Masonry and finishes | 1,20,00,000 | 0 | 0 | 0 | 10 | 5 | 7,00,000 |
| WP4 MEP services | 40,00,000 | 5 | 0 | 1,00,000 | 10 | 5 | 3,00,000 |
| Total | 4,00,00,000 |  |  |  |  |  |  |

File: data/benchmark_case_work_packages.csv. Assumptions: all values cumulative; actual % is physical progress against budgeted scope; one baseline.

# 4. Manual calculations (working shown; ₹ lakh = ₹1,00,000)

Period 1 — 31-Jan-2026

- PV = 80×1.00 + 160×0.40 + 120×0 + 40×0.05 = 80 + 64 + 0 + 2 = 146.00 lakh

- EV = 80×1.00 + 160×0.30 + 120×0 + 40×0 = 80 + 48 = 128.00 lakh

- AC = 84 + 52 + 0 + 1 = 137.00 lakh

- CV = 128 − 137 = −9.00 lakh; SV = 128 − 146 = −18.00 lakh

- CPI = 128/137 = 0.934307; SPI = 128/146 = 0.876712

- EAC(A) = BAC/CPI = 400 × 137/128 = 428.125 lakh; ETC = 428.125 − 137 = 291.125; VAC = −28.125; overrun 28.125/400 = 7.03125%

- EAC(B) = 137 + (400 − 128)/(CPI×SPI); CPI×SPI = (128×128)/(137×146) = 16,384/20,002 = 0.819118; 272/0.819118 = 272×20,002/16,384 = 332.064453; EAC(B) = 469.064453 lakh; ETC 332.064453; VAC −69.064453; overrun 17.266113%

- EAC(C) = 137 + 272 = 409.00 lakh; ETC 272; VAC −9; overrun 2.25%

- TCPI to BAC = (400 − 128)/(400 − 137) = 272/263 = 1.034221

- TCPI to EAC: A = 272/291.125 = 0.934307 (= CPI ✓); B = 272/332.064453 = 0.819118 (= CPI×SPI ✓); C = 272/272 = 1 ✓

Period 2 — 28-Feb-2026

- PV = 80 + 160×0.70 + 120×0.10 + 40×0.10 = 80 + 112 + 12 + 4 = 208.00 lakh

- EV = 80 + 160×0.55 + 120×0.05 + 40×0.05 = 80 + 88 + 6 + 2 = 176.00 lakh

- AC = 84 + 98 + 7 + 3 = 192.00 lakh

- CV = −16.00 lakh; SV = −32.00 lakh; CPI = 176/192 = 0.916667; SPI = 176/208 = 0.846154

- EAC(A) = 400 × 192/176 = 436.363636 lakh; ETC 244.363636; VAC −36.363636; overrun 9.090909%

- EAC(B): CPI×SPI = 30,976/39,936 = 0.775641; 224/0.775641 = 224×39,936/30,976 = 288.793388; EAC(B) = 480.793388 lakh; overrun 20.198347%

- EAC(C) = 192 + 224 = 416.00 lakh; overrun 4.00%

- TCPI to BAC = 224/208 = 1.076923

Weighting check. An unweighted average of Period 2 actual percentages, (100+55+5+5)/4 = 41.25%, would give EV = 165 lakh — ₹11 lakh (6.3%) below the correct budget-weighted 176 lakh. The dashboard must give 176.

Independent cross-checks of the paper working. (a) benchmark/independent_benchmark_calc.py recomputes everything with exact fractions and imports no dashboard code (enforced by a test that inspects its import statements); (b) benchmark/benchmark_workbook.xlsx computes the same with plain spreadsheet formulas (73 formulas, recalculated in LibreOffice, 0 errors). All three agree to the last digit shown above.

# 5. Dashboard calculation procedure

The dashboard values were produced through the same path a user follows: read the CSV → map columns → validate → derive PV/EV/AC → calculate (tests/test_benchmark.py, benchmark/compare_with_dashboard.py). The same project was also entered (i) as pre-calculated PV/EV/AC and (ii) as project-level percentages (36.5%/32% and 52%/44%), to check the three input modes agree. In the browser, the benchmark PV/EV/AC were entered through the manual-entry table and loaded; the Overview showed CPI 0.917, SPI 0.846, EAC(A) ₹436.36 lakh and TCPI 1.077 for Period 2, matching Section 4.

# 6. Comparison

Tolerances: money ±₹0.01 (one paisa); indices ±1×10⁻⁹; percentages ±1×10⁻⁷. Values were compared at full precision — no rounding before comparison.

- work_package input mode: 54 values compared, 54 PASS, 0 FAIL; max |difference| = 7.45e-09

- precalc input mode: 54 values compared, 54 PASS, 0 FAIL; max |difference| = 7.45e-09

- progress input mode: 54 values compared, 54 PASS, 0 FAIL; max |difference| = 7.45e-09

Full table (work-package input mode; the other two modes give identical results):

| Metric | Method | Period | Manual result | Dashboard result | Difference | Tolerance | Status |
| --- | --- | --- | --- | --- | --- | --- | --- |
| BAC |  | 2026-01-31 | 40,000,000.0000 | 40,000,000.0000 | 0.00e+00 | 0.01 | PASS |
| PV |  | 2026-01-31 | 14,600,000.0000 | 14,600,000.0000 | 0.00e+00 | 0.01 | PASS |
| EV |  | 2026-01-31 | 12,800,000.0000 | 12,800,000.0000 | 0.00e+00 | 0.01 | PASS |
| AC |  | 2026-01-31 | 13,700,000.0000 | 13,700,000.0000 | 0.00e+00 | 0.01 | PASS |
| CV |  | 2026-01-31 | -900,000.0000 | -900,000.0000 | 0.00e+00 | 0.01 | PASS |
| SV |  | 2026-01-31 | -1,800,000.0000 | -1,800,000.0000 | 0.00e+00 | 0.01 | PASS |
| CPI |  | 2026-01-31 | 0.9343065693 | 0.9343065693 | 4.31e-11 | 1e-09 | PASS |
| SPI |  | 2026-01-31 | 0.8767123288 | 0.8767123288 | -3.29e-11 | 1e-09 | PASS |
| TCPI_BAC |  | 2026-01-31 | 1.0342205323 | 1.0342205323 | 1.94e-11 | 1e-09 | PASS |
| EAC | A | 2026-01-31 | 42,812,500.0000 | 42,812,500.0000 | 0.00e+00 | 0.01 | PASS |
| ETC | A | 2026-01-31 | 29,112,500.0000 | 29,112,500.0000 | 0.00e+00 | 0.01 | PASS |
| VAC | A | 2026-01-31 | -2,812,500.0000 | -2,812,500.0000 | 0.00e+00 | 0.01 | PASS |
| OVERRUN | A | 2026-01-31 | 2,812,500.0000 | 2,812,500.0000 | 0.00e+00 | 0.01 | PASS |
| OVERRUN_PCT | A | 2026-01-31 | 7.03125000 | 7.03125000 | 0.00e+00 | 1e-07 | PASS |
| TCPI_EAC | A | 2026-01-31 | 0.9343065693 | 0.9343065693 | 4.31e-11 | 1e-09 | PASS |
| EAC | B | 2026-01-31 | 46,906,445.3125 | 46,906,445.3125 | 0.00e+00 | 0.01 | PASS |
| ETC | B | 2026-01-31 | 33,206,445.3125 | 33,206,445.3125 | 0.00e+00 | 0.01 | PASS |
| VAC | B | 2026-01-31 | -6,906,445.3125 | -6,906,445.3125 | 0.00e+00 | 0.01 | PASS |
| OVERRUN | B | 2026-01-31 | 6,906,445.3125 | 6,906,445.3125 | 0.00e+00 | 0.01 | PASS |
| OVERRUN_PCT | B | 2026-01-31 | 17.26611328 | 17.26611328 | 5.00e-11 | 1e-07 | PASS |
| TCPI_EAC | B | 2026-01-31 | 0.8191180882 | 0.8191180882 | -8.82e-12 | 1e-09 | PASS |
| EAC | C | 2026-01-31 | 40,900,000.0000 | 40,900,000.0000 | 0.00e+00 | 0.01 | PASS |
| ETC | C | 2026-01-31 | 27,200,000.0000 | 27,200,000.0000 | 0.00e+00 | 0.01 | PASS |
| VAC | C | 2026-01-31 | -900,000.0000 | -900,000.0000 | 0.00e+00 | 0.01 | PASS |
| OVERRUN | C | 2026-01-31 | 900,000.0000 | 900,000.0000 | 0.00e+00 | 0.01 | PASS |
| OVERRUN_PCT | C | 2026-01-31 | 2.25000000 | 2.25000000 | 0.00e+00 | 1e-07 | PASS |
| TCPI_EAC | C | 2026-01-31 | 1.0000000000 | 1.0000000000 | 0.00e+00 | 1e-09 | PASS |
| BAC |  | 2026-02-28 | 40,000,000.0000 | 40,000,000.0000 | 0.00e+00 | 0.01 | PASS |
| PV |  | 2026-02-28 | 20,800,000.0000 | 20,800,000.0000 | 0.00e+00 | 0.01 | PASS |
| EV |  | 2026-02-28 | 17,600,000.0000 | 17,600,000.0000 | 0.00e+00 | 0.01 | PASS |
| AC |  | 2026-02-28 | 19,200,000.0000 | 19,200,000.0000 | 0.00e+00 | 0.01 | PASS |
| CV |  | 2026-02-28 | -1,600,000.0000 | -1,600,000.0000 | 0.00e+00 | 0.01 | PASS |
| SV |  | 2026-02-28 | -3,200,000.0000 | -3,200,000.0000 | 0.00e+00 | 0.01 | PASS |
| CPI |  | 2026-02-28 | 0.9166666667 | 0.9166666667 | -3.33e-11 | 1e-09 | PASS |
| SPI |  | 2026-02-28 | 0.8461538462 | 0.8461538462 | -4.62e-11 | 1e-09 | PASS |
| TCPI_BAC |  | 2026-02-28 | 1.0769230769 | 1.0769230769 | 2.31e-11 | 1e-09 | PASS |
| EAC | A | 2026-02-28 | 43,636,363.6364 | 43,636,363.6364 | 7.45e-09 | 0.01 | PASS |
| ETC | A | 2026-02-28 | 24,436,363.6364 | 24,436,363.6364 | 0.00e+00 | 0.01 | PASS |
| VAC | A | 2026-02-28 | -3,636,363.6364 | -3,636,363.6364 | -4.66e-09 | 0.01 | PASS |
| OVERRUN | A | 2026-02-28 | 3,636,363.6364 | 3,636,363.6364 | 4.66e-09 | 0.01 | PASS |
| OVERRUN_PCT | A | 2026-02-28 | 9.09090909 | 9.09090909 | 9.10e-12 | 1e-07 | PASS |
| TCPI_EAC | A | 2026-02-28 | 0.9166666667 | 0.9166666667 | -3.33e-11 | 1e-09 | PASS |
| EAC | B | 2026-02-28 | 48,079,338.8430 | 48,079,338.8430 | 7.45e-09 | 0.01 | PASS |
| ETC | B | 2026-02-28 | 28,879,338.8430 | 28,879,338.8430 | 7.45e-09 | 0.01 | PASS |
| VAC | B | 2026-02-28 | -8,079,338.8430 | -8,079,338.8430 | -7.45e-09 | 0.01 | PASS |
| OVERRUN | B | 2026-02-28 | 8,079,338.8430 | 8,079,338.8430 | 7.45e-09 | 0.01 | PASS |
| OVERRUN_PCT | B | 2026-02-28 | 20.19834711 | 20.19834711 | 3.80e-11 | 1e-07 | PASS |
| TCPI_EAC | B | 2026-02-28 | 0.7756410256 | 0.7756410256 | 4.10e-11 | 1e-09 | PASS |
| EAC | C | 2026-02-28 | 41,600,000.0000 | 41,600,000.0000 | 0.00e+00 | 0.01 | PASS |
| ETC | C | 2026-02-28 | 22,400,000.0000 | 22,400,000.0000 | 0.00e+00 | 0.01 | PASS |
| VAC | C | 2026-02-28 | -1,600,000.0000 | -1,600,000.0000 | 0.00e+00 | 0.01 | PASS |
| OVERRUN | C | 2026-02-28 | 1,600,000.0000 | 1,600,000.0000 | 0.00e+00 | 0.01 | PASS |
| OVERRUN_PCT | C | 2026-02-28 | 4.00000000 | 4.00000000 | 0.00e+00 | 1e-07 | PASS |
| TCPI_EAC | C | 2026-02-28 | 1.0000000000 | 1.0000000000 | 0.00e+00 | 1e-09 | PASS |

# 7. Discrepancies and defects found

No numerical discrepancy was found between the manual benchmark and the dashboard (maximum |difference| = ₹7.5×10⁻⁹, floating-point representation). Because a first-run match does not prove the tests can detect errors, mutation testing was performed (Section 12). The following genuine defects and findings arose during development and testing:

| # | Found by | Defect / finding | Root cause | Correction | Retest |
| --- | --- | --- | --- | --- | --- |
| D1 | Unit test run | Test “expected file independent of src” failed although the benchmark script imports nothing from the app | Test searched the text for “from src” and matched a phrase in the script’s docstring (defect in the test, not the app) | Test rewritten to inspect actual import statements (AST) | Pass |
| D2 | Browser test | After a rejected upload, the next (valid) file loaded under the project name typed for the rejected file, not the name in the new file | Settings widgets kept their state across files (same widget keys) | Widgets keyed to the specific file and mode | Pass: second upload took the file’s own name |
| D3 | Browser test (screenshot review) | A non-numeric AC produced two errors for one cell (“not a number” and “missing”) | Missing-value check re-flagged a cell already rejected by parsing | Missing check skips cells already in error | Pass: 5 errors instead of 6 |
| D4 | Screenshot review | A warning named the internal field planned_pct instead of the user’s column planned_progress_pct | Internal column name passed as field label | Mapped to user-facing names | Pass |
| D5 | Data generation | Progress-based demo file EV for 31-Aug-2026 = ₹7,02,50,000.40 vs ₹7,02,50,000 from WP data | Percentages stored to 6 decimals | Not a code defect; documented as limitation (rounded % inputs lose precision) | Recorded |
| D6 | Screenshot review | Signboard clipped, KPI labels truncated, BAC/EAC chart labels overlapping, CPI/SPI axis cutting off the 1.00 line, preview dates showing “00:00:00” | Layout defaults | Labels shortened, annotations repositioned, axis range includes 1.00 and the critical line, dates formatted | Pass (screenshots in reports/screenshots/) |

# 8–10. Root causes, corrections and retest

Given per defect in Section 7. After all corrections the complete suite was rerun: 79 passed, 0 failed (reports/test_results.txt), and the browser run was repeated (reports/browser_test_log.txt).

# 11. Edge-case and workflow testing

| Case | Expected behaviour | Evidence | Result |
| --- | --- | --- | --- |
| AC = 0 | CPI undefined (not 0), reason shown; CV defined | test_cpi_undefined_when_ac_zero | Pass |
| PV = 0 | SPI undefined | test_spi_undefined_when_pv_zero | Pass |
| EV = 0 | CPI = 0; EAC A and B undefined; C defined | test_zero_earned_value_… | Pass |
| AC = BAC with work remaining | TCPI to BAC undefined (“no longer possible”) | test_tcpi_bac_undefined_when_ac_equals_bac | Pass |
| AC > BAC | TCPI to BAC undefined, never negative | test_tcpi_bac_undefined_when_budget_exceeded | Pass |
| EAC below / above BAC | VAC positive / negative | test_eac_below_bac…, test_eac_above_bac | Pass |
| Project complete (EV = PV = BAC) | SPI = 1, ETC = 0, TCPI N/A | test_project_completion | Pass |
| Missing reporting period | Warning; chart line broken | test_missing_monthly_period…; with_gap_breaks | Pass |
| Negative cumulative AC / BAC | Blocking error | test_negative_cumulative_ac_is_error, test_missing_project_name_and_bad_bac | Pass |
| Progress < 0 or > 100 | Blocking error | test_progress_out_of_range | Pass |
| Decreasing cumulative values | Warning, value unchanged | test_decreasing_cumulative_progress… | Pass |
| Cost with no new progress | No error | test_cost_without_progress_is_not_an_error | Pass |
| Cumulative and period AC inconsistent | Warning; cumulative used, never summed | test_cumulative_and_period_ac_inconsistent | Pass |
| Missing value | Error, never zero | test_missing_value_is_error_not_zero | Pass |
| Unweighted WP average | Budget-weighted EV used | test_work_package_ev_is_budget_weighted… | Pass |
| All 4 forecast methods, all 9 dates, all units | Render without error; method D “N/A” until ETC entered | tests/test_app.py | Pass |
| Invalid file upload (browser) | Errors listed by row; no load button; current project unchanged | browser log | Pass |
| Valid CSV upload (browser) | Loads after confirmation; CPI 0.947 | browser log | Pass |
| Manual entry → load (browser) | Benchmark P2 values reproduced | browser log | Pass |
| Editing a single cell in the manual table (browser) | Edit re-validates | Scripted edit did not register in the canvas grid | Not verified — team to check by hand (2 min): change an AC to −5 and confirm a blocking error appears |
| Upload ↔ manual entry equivalence | Identical results | test_manual_entry_and_upload_give_identical_results | Pass |
| Older library versions | Suite passes | pandas 2.2.3 / Streamlit 1.50 / Plotly 5.24 venv: 79 passed | Pass |

# 12. Mutation testing (can the tests catch typical errors?)

Each error below was injected into a temporary copy of the code; the suite was run; the copy discarded.

| Injected error | Tests failing |
| --- | --- |
| SPI inverted (PV/EV) | 8 |
| CV sign reversed (AC − EV) | 6 |
| EAC(B) written as BAC/(CPI×SPI) | 5 |
| TCPI to BAC forced to 1 | 4 |
| EV from an unweighted average of WP percentages | 2 |
| Period AC used as if cumulative | 1 |
| CPI returned as 0 when AC = 0 | 2 |

All seven were detected.

# 13. Remaining limitations of the validation

- One synthetic benchmark (two periods) — not a real project; practitioner review is still recommended.

- Method D (independent ETC) is checked by unit and interface tests, not by the paper benchmark (it is a user input, not a formula).

- Charts and commentary were checked by inspection and interface tests, not against an independent reference.

- Manual-table cell editing in the browser not verified by automation (Section 11).

# 14. Conclusion

For the benchmark case, all 54 benchmark values per input mode (162 comparisons) match the independently prepared results within one paisa / 10⁻⁹, with no discrepancies; undefined and edge cases are reported as undefined or flagged rather than shown as numbers; and the test suite detects all seven typical formula errors injected. Subject to the team’s own paper verification (Section 15), the calculation engine is considered validated for the scope tested.

# 15. Team verification sign-off

| Check | Done by | Date | Signature |
| --- | --- | --- | --- |
| Period 1 recalculated on paper without the tool; matches Section 4 |  |  |  |
| Period 2 recalculated on paper without the tool; matches Section 4 |  |  |  |
| python -m pytest run on a team laptop: 79 passed |  |  |  |
| Manual-table cell edit check (Section 11) done |  |  |  |
| Any discrepancy found by the team recorded here and in the AI usage log |  |  |  |